## UAT
User Acceptance Test Plan
Project Name |  | E-commerce Project
Group Name |  | CELL
Name of Tester/s: |  | Aiden, Abby, Sara
Test ID | Description of test cases | Steps To Execute | Test data | Expected Results/Behaviour | Observed Results/Behaviour | Pass/Fail | Defect/Comments/Additions
HOME PAGE
1 | Page Reponse Time | Open Developer Tools, open networking, refresh page |  | Page fully loads with all content within 2-3 Secounds | Pages contents loaded in 1.52 seconds | pass
2 | Hover animation on the "Features Of Our Watches" section | navigate to the features section, Hover curser on the fitness tracking, alerts and notifications, messages and bluetooth boxes |  | All Hover animations activate when the curser is above the the box | All boxes had a successful hover animation when curser was hovering them | pass
3 | Testimonial foward carousel button | navigate to the testimonial section, click both the left and right arrow buttons displayed under the carousel |  | Once the left or right arrow button is clicked the above box will display an animation to change the box to next or previous box. | Once clicked the left arrow button changed the box to the prevoius box with an animation. The right arrow butto when clicked changed the box to the next box in the carousel | pass
4 | Test the Phone display changes to the correct display proportions | Open Develpper tools and change the page display to the phone option and navigate the page |  | Page successfully changes proportions to accoudate the display | Page displayed as phone and successfully accommodated the display by changing proportions | pass
5 | Contact Us button redirects to the contacts page | Click the Contact us button on the Slider Section card |  | On clicking the button the page should redirect the user to a contacts page | On clicking the button the page didn’t redirect but instead refreshed | fail | Button redircets the user to the home page rather than the contacts page
WATCHES PAGE
1 | Each Product card when clicked displays the product | Click each product card link |  | The Product card link will open a page on the product with details | The Product cards when clicked redirected to the watches page rather than the watch details | fail | The Product cards redirect the user to the watches page instead of
2 | Header Links on watches page redirect the user to the linked page | Click on each link displayed on the header |  | The Header links redirect the user to the page listed | Each link when clicked redircts you to the page it listed as a link | pass
3 | View all Button clicked changes the viewing display of the products | Click on the View All link under all the products |  | the View All button will change the layout and display of the product cards listed | The View all button when clicked redirts you to the watches page without changing the layout of the product cards | fail | The View All button Refreshes the watches page instead of changing the layout or redirecting the user
4 | Cart Icon Button takes the user to the cart page | Click the Cart Icon Button in the top right corner of the header |  | The Cart Button redirects the user to the Cart page | The Cart Button when clicked reloads the current page | fail | Cart Button Reloads the page the user is currently on instead of redirecting to the Cart page.
ABOUT PAGE
1
2
3
4
5
CONTACT US PAGE
1
2
3
4
5
ORDERS PAGE
1
2
3
4
5