## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Gantt Chart
Gantt Chart for E-commerce Project
CELL |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Abby, Aiden, Sara
Project Start Date: | 2026-02-25 |  |  |  |  | April | [20 empty] | May | [27 empty] | June
Scrolling Increment: | 50 | time axis 2026-04-16 to 2026-06-10
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-04-16 to 2026-06-10
Iteration 1
Complete all tasks for Iteration 1 in a GitHub repository | Goal | All Members | 100% | 2026-02-25 | 1
Meeting #1 | Goal | All Members | 100% | 2026-02-25 | 1
Stakeholder Register | On Track | All Members | 100% | 2026-02-25 | 5
Meeting #2 | Goal | All Members | 100% | 2026-03-04 | 1
Create Personas (3 in total) | On Track | All Members | 100% | 2026-03-04 | 7
Meeting #3 | Goal | All Members | 100% | 2026-03-10 | 1
Review Personas | On Track | All Members | 100% | 2026-03-10 | 8
Create and update README file | On Track | All Members | 100% | 2026-03-10 | 8
Individual Progress Report | On Track | All Members | 100% | 2026-03-10 | 8
Meeting #4 | Goal | All Members | 100% | 2026-03-11 | 1
Complete all tasks for Iteration 1 and submitted Progress Reports | Milestone | All Members | 100% | 2026-03-18 | 1
Iteration 2
Complete all tasks for Iteration 2 | Goal | All Members | 100% | 2026-03-18 | 1
Meeting #1 | Goal | All Members | 100% | 2026-03-18 | 1
Research - Gantt Charts, Kanban Board | On Track | All Members | 100% | 2026-03-18 | 7
Meeting #2 | Goal | All Members | 100% | 2026-03-25 | 1
Create a Kanban Board and tasks / issues - for self task assignment | On Track | All Members | 100% | 2026-03-25 | 7
Create and update detailed Gantt Chart with Iteration 1 tasks | On Track | All Members | 100% | 2026-03-31 | 2
Meeting #3 | Goal | All Members | 100% | 2026-04-01 | 1
BREAK |  | All Members | 100% | 2026-04-06 | 14
Meeting #4 | Goal | All Members | 100% | 2026-04-22 | 1 | 2026-04-22: 2
Update detailed Gantt Chart and add Iteration 2 tasks | On Track | All Members | 100% | 2026-04-22 | 6
Commit and complete Resource Requirement List | On Track | All Members | 100% | 2026-04-22 | 6
Individual Progress Report | On Track | All Members | 100% | 2026-04-22 | 8
Update README file with Iteration 2 details | On Track | All Members | 100% | 2026-04-22 | 8
As a group, test and review new changes to README file | On Track | All Members | 100% | 2026-04-22 | 8
Complete all tasks for Iteration 2 and submit Progress Reports | Milestone | All Members | 100% | 2026-04-29 | 1 | bar: 2026-04-29
Iteration 3
Complete all tasks for Iteration 3 in a GitHub repository | Goal | All Members | 100% | 2026-04-29 | 1 | 2026-04-29: 2
Meeting #1 | Goal | All Members | 100% | 2026-04-29 | 1 | 2026-04-29: 2
Meeting #2 | Goal | All Members | 100% | 2026-05-06 | 1 | 2026-05-06: 2
Push website files to the GitHub Repository | On Track | All Members | 100% | 2026-05-06 | 2
Publish Website | On Track | All Members | 100% | 2026-05-06 | 6
Meeting #3 | Goal | All Members | 100% | 2026-05-13 | 1 | 2026-05-13: 2
Push Risk Register and add relevant risks relating to the project | On Track | All Members | 100% | 2026-05-13 | 6
Meeting #4 | Goal | All Members | 100% | 2026-05-20 | 1 | 2026-05-20: 2
Rearrange GitHub Repository (website to /docs), check integration | On Track | All Members | 100% | 2026-05-20 | 6
Push User Acceptance Test Results and add from notes | On Track | All Members | 100% | 2026-05-20 | 6
Update README file with Iteration 3 details | On Track | All Members | 100% | 2026-05-20 | 6
Individual Progress Report | On Track | All Members | 100% | 2026-05-20 | 6
Complete all tasks for Iteration 3 and submit Progress Reports | Milestone | All Members | 100% | 2026-05-27 | 1 | bar: 2026-05-27
To add more data, Insert new rows ABOVE this one

## Light
PROJECT TITLE
CELL |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project Start Date: | 2026-02-25 |  |  |  |  | February | [6 empty] | March | [27 empty] | April
Scrolling Increment: | 0 | time axis 2026-02-25 to 2026-04-21
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-02-25 to 2026-04-21
Iteration 1
Complete all tasks for Iteration 1 in a GitHub repository | Goal | All Members | 100% | 2026-02-25 | 1 | 2026-02-25: 2
Stakeholder Register | High Risk | Aiden | 100% | 2026-02-25 | 5
Create Personas (3 in total) | Med Risk | All Members | 100% | 2026-03-04 | 7
Review Personas | Low Risk | All Members | 100% | 2026-03-10 | 8
Create and update README file | Med Risk | Aiden, Sara | 100% | 2026-03-10 | 8
Individual Progress Report | High Risk | All Members | 100% | 2026-03-10 | 8
Complete all tasks for Iteration 1 and submitted Progress Reports | Milestone | All Members | 100% | 2026-03-18 | 1 | bar: 2026-03-18
Iteration 2
Complete all tasks for Iteration 2 | Goal | All Members | 55% | 2026-03-18 | 1 | 2026-03-18: 2
Create a Kanban Board and task notes for self assignment | Milestone | Sara | 100% | 2026-03-25 | 1 | bar: 2026-03-25
Create and update detailed Gantt Chart with Iteration 1 tasks | High Risk | Aiden | 100% | 2026-03-31 | 2
Update detailed Gantt Chart and add Iteration 2 tasks | High Risk | Sara | 50% | 2026-04-22 | 6
Commit and complete Resource Requirement List | Med Risk | Aiden |  | 2026-04-22 | 6
Individual Progress Report | High Risk | All Members |  | 2026-04-22 | 7
Update README file with Iteration 2 details | Med Risk | All Members |  | 2026-04-22 | 6
As a group, test and review new changes to README file | Goal | All Members |  | 2026-04-28 | 1
Complete all tasks for Iteration 2 and submitted Progress Reports | Milestone | All Members |  | 2026-04-28 | 1
Iteration 3
Task 1 |  |  |  | 2026-05-01 | 15
Task 2 |  |  |  | 2026-05-15 | 5
Task 3 | Milestone |  |  | 2026-06-26 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
Agile Projects
CELL |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2026-02-25 |  |  |  |  | February | [6 empty] | March | [27 empty] | April
Scrolling Increment: | 0 | time axis 2026-02-25 to 2026-04-21
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Iteration 1 |  | All members | 100% | 2026-02-25 | 25
Complete all tasks for iteration 1 | Goal | All members | 100% | 2026-05-26 | 3
Group Metting #1 | Med Risk | All members | 100% | 2026-02-25 | 1
Create and set up Repository for Project | High Risk | All members | 100% | 2026-02-25 | 1
Stakeholder Register | High Risk | All members | 100% | 2026-02-25 | 1
Group Meeting #2 | High Risk | All members | 100% | 2026-03-04 | 4
Create persona #1 | Med Risk | All members | 100% | 2026-03-04 | 6
Create persona #2 | Med Risk | Abby | 100% | 2026-03-04 | 6
Create persona #3 | Med Risk | Aiden | 100% | 2026-03-04 | 6
Group Meeting #3 | Med Risk | Sara | 100% | 2026-03-10 | 10
Review of Each Person | Med Risk | All members | 100% | 2026-03-10 | 4 | bar: F
Group Meeting #4 | Med Risk | All members | 100% | 2026-03-11 | 3
Progress report | Med Risk | All members | 100% | 2026-03-11 | 7
Complete Read me File within iteration 1 | Med Risk | All members | 100% | 2026-03-11 | 7
Task 1 | High Risk |  |  | 2026-03-04 | 10
Task 2 | On Track |  |  | 2026-03-06
Task 3 | Low Risk |  | 33% | 2026-03-11 |  | S: 2; S: 2; M: 2
Task 4 | Milestone |  |  | 2026-03-13 | 1
Task 5 |  |  |  | 2026-03-14 | 24
TITLE 3
Task 1 | On Track |  |  | 2026-06-10 | 4
Task 2 | Med Risk |  |  | 2026-06-13 | 14
Task 3 | On Track |  |  | 2026-06-28 | 6
Task 4 | Goal |  |  | 2026-04-04 | 3
Task 5 | Low Risk |  |  | 2026-03-04 | 19
TITLE 4
Task 1 |  |  |  | 2026-04-07 | 15
Task 2 |  |  |  | 2026-04-21 | 5
Task 3 | Milestone |  |  | 2026-06-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
CELL |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2026-02-25 |  |  |  |  | February | [6 empty] | March | [27 empty] | April
Scrolling Increment: | 0 | time axis 2026-02-25 to 2026-04-21
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-02-25 to 2026-04-21
Iteration 1 |  |  |  | 2026-02-25 | 25
Complete all tasks for iteration 1 | Goal | Name | 25% | 2026-05-26 | 3
Group Metting #1 | Med Risk | All members |  | 2026-02-25 | 1
Create and set up Repository for Project | High Risk | All members | 50% | 2026-02-25 | 1
Stakeholder Register | High Risk | All members |  | 2026-02-25 | 1
Group Meeting #2 | High Risk | All members | 10% | 2026-03-04 | 1
TITLE 2 |  |  |  |  | 0
Task 1 | High Risk |  | 60% | 2026-06-01 | 13
Task 2 | On Track |  | 50% | 2026-06-03 | 9
Task 3 | Low Risk |  | 33% | 2026-06-08 | 11
Task 4 | Milestone |  |  | 2026-06-10 | 1
Task 5 |  |  |  | 2026-06-11 | 24
TITLE 3
Task 1 | On Track |  |  | 2026-06-10 | 4
Task 2 | Med Risk |  |  | 2026-06-13 | 14
Task 3 | On Track |  |  | 2026-06-28 | 6
Task 4 | Goal |  |  | 2026-07-02 | 3
Task 5 | Low Risk |  |  | 2026-03-04 | 19
TITLE 4
Task 1 |  |  |  | 2026-07-05 | 15
Task 2 |  |  |  | 2026-07-19 | 5
Task 3 | Milestone |  |  | 2026-08-30 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one